People First of Alabama State Work Plan

State Call People First of Alabama

12/18/14

11:00 AM CST-Noon PM EST

Participating:  Nikki Dawson, Brittany Gore, Chris Ballard, Susan Ellis, Chaqueta Stuckey, Glenda Hyman Singletary, Juliana Huerena, Vicki Hicks Turnage

Agenda

- Reviewed Work Plan to assure inclusion of contract requirements

- Identified two ways SABE and OCSS can support your plan activities

- Reminder to complete Surveys- Evaluation and 2015 Plans

- Questions and Answers

State Technical Assistance Project Work Plan

Goal: Develop and Implement a State Technical Assistance Needs and Plan to strengthen the organization

Measurable Outcome(s): Participating State Self Advocacy Organizations develop, implement and monitor an individualized plan for strengthening their organizations and local groups capacity to run their organizations through partnerships with SABE, DD Network, and community organizations.

State Name: People First of Alabama

Contractual requirements in red: Alabama has addressed all of the required contractual areas.

| Objective | Action Steps | 1* October-December | 2* January-March | 3* April-June | 4* July-September |
| --- | --- | --- | --- | --- | --- |
| To Develop or Enhance partnerships with DD Partners in your state | Host a retreat to identify ways and timeframes on activities that you can work together on. Completed in 2014 Working with ADAP the DMH and DD Council on Employment First campaign Develop an executive order to support employment first Education on employment issues Work with DD council on Young Emerging Leaders Grant Ongoing Expanding contact with youth in state transition conference and youth summit at Sanford University in the summertime Will talk to Arizona about logistics for youth summit Create a statewide Advisory PF Board with DD partner (and other disability allies) participation verbal agreement Start regular communication with UAB UCEDD; develop mutual projects PF has a member on the advisory board now, it was a big victory Letters to UAB, DD council, and ADAP leaders that confirm agreements to provide support and collaboration will be sent from PF of Alabama Letters will be completed by the end of December | October 2014 Oct. 2014 Oct. 2014 |  |  | Aug. 2014 Ongoing Ongoing |
| Develop opportunities to create excitement for greater participation in self-advocacy topics | 2014 PF state conference presentations (what about 2015 conference? This could count as a grassroots event) 2015 conference is in the works Produce a quarterly state newsletter for DD partners, supporters, members. Distribute throughout the state January done will write one for each quarter about what is going on Will send copies to Chaqueta Consider initiating a “Meaningful Day” retreat with collaboration from DMH, DD council, ADAP, UAB, and community providers Starting February will help each chapter to develop examples of “Meaningful day” events Consider funding a statewide “Youth Summit” to develop leaders in self-advocacy to participate in civic and community roles In the works, committee in place | Aug. 2014 Sept 2014 to Oct. 2015 | Jan. 2015 Jan 2105 |  |  |
| Increase connections to the grassroots to promote self- advocacy efforts | Host 1 per quarter (8 for year) Grassroots Events with a partner to promote one or more of the issues identified in the needs assessment: Employment First/voting rights/human rights/self advocacy membership recruitment of Individuals with Disabilities, Olmstead, Marriage Penalty, Community Living, Transportation, Affordable Housing, relationships Needs to be 8 events Presented 3 events this quarter (October) Youth Summit lead, focus on Bullying PF statewide conference 2015 Legislative day with other DD agencies to rally in Montgomery Monitoring at sheltered (subminimum wage) Workshops Person Centered Planning (help self advocates about Meaningful day) Educational training for parents for students with DD Transition conference, training to high school students Increase board participation with local chapters throughout the state by travelling and using technology. Chris is working on calling around the state and in person visits to 3 regions to create new chapters and fortify existing chapters 3. Involve local chapters in decision making process for statewide campaigns using social media, mailings, email communication, website, telephone conferences and travel Reaching out and ongoing throughout the year | Oct 2014-Sept 2015 Sept.2014 ongoing to Oct 2015 Sept. 2014 and ongoing |  |  |  |
| Enhance the state leadership skills in providing peer to peer technical assistance in their state and the region | Participate in Quarterly Advisory Committee meetings for OCSS Attend Face to Face Meetings of the Webinar Present on at least one OCSS Webinar (What topic would you like to present?) Partnership with the department of mental health Employment Submit at least 2 Vlogs on issues of concern (What issue will your vlog address?) Help with accessing technology (access to equipment, transportation to community locations for access {libraries}, how to use technology, maintain websites that are useful for everyone How to get transportation to locations Participate in OCSS Webinar | Completed Sept. 2014 |  |  |  |
| Establishment of state structure to maintain connections with grassroots | 1. Refer to our strategic plan and funding (financial plan) for a state structure that supports grassroots issues 2. Secure at least one grant per year with the support of your partners (Do you have a project identified in your strategic plan?) The YEL (Young Emerging Leaders) funded for 2 years DMH with Employment First no money attached to project or in kind benefit to organization- a part of contract with DMH Suggestion made that the organization explore grants that might bring in kind support to organization, such as help teach people how to post to the website 3. Utilize our non­profit status to access prominent donations. Explore corporate giving programs like Drummond Coal or others in state. 4. Use technology and social media and regular direct communications with chapters by state office staff and PF Board of directors and executive committee | Oct. 2014 to Sept. 2015 |  |  |  |

How can the OCSS Team or others on the Advisory Committee help you with your plan?

Identify two ways.

1.) Technical assistance with the youth summit

2.) Assist us to learn more about technology

Questions and Answers:

Need Alabama to complete the following surveys:

Evaluation of year 1

2015 activities year 2 to continue based on contract